## Slide 1
Hero Title
The Q4 capacity plan covers baseline demand, but a long-lead actuator constraint leaves the launch buffer exposed.
Body Narrative
Northstar launch · weeks 38–45 · supplier feed closed 2026-09-23 18:00 UTC · demand scenario P70 · allocation review for Operations and Procurement.
P70 capacity headroom
2.7%
Actuator lead time
116 days
Confirmed capacity · W38 to W45
120000 units → 142000 units
Chart: Demand by week
| W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45
Demand by week | 112000 | 117000 | 121000 | 125000 | 130000 | 134000 | 139000 | 144000
Chart: Confirmed capacity by week
| W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45
Confirmed capacity by week | 120000 | 124000 | 126000 | 130000 | 132000 | 136000 | 140000 | 142000
Body Narrative
Confirmed capacity exceeds the P70 baseline by 2.7% in aggregate. Another 27,500 actuator units remain unconfirmed across two suppliers; the 116-day lead time makes that small buffer fragile. Do not treat planned capacity as firm supply until the dated allocation lands.
Risk Callout
Reserve critical actuator supply before releasing the balance
Aggregate headroom hides a concentrated 16-week lead-time constraint. Do not treat unconfirmed supplier allocation as available capacity.
At risk
Key Takeaway
Next step: reserve 18,000 qualified actuators now, then release the remaining build only after supplier NC-8841 confirms its dated allocation.
Supplier / part | Committed | Unconfirmed | Lead time | Decision evidence
Northstar Motion / AX-8841 | 72000 | 18000 | 116 days | Reserve qualified stock now
Apex Controls / actuator-22B | 54000 | 9500 | 98 days | Date-coded allocation pending
Orion Systems / NX-041-REV-C | 39000 | 0 | 42 days | Capacity confirmed through W45
Allocation decision path
Reconcile
P70 demand
Reserve
qualified
actuators
Confirm
date-coded
allocation
Release
remaining
build